# NORTHERN RAILWAY - DIVISIONAL OPERATING CIRCULAR

REF: NR/OPTG/BLOCK-REQ/2026/W35 | DATE: 27-AUG-2026

# 1. Engineering & Track Maintenance Work Proposals

The following track tamping, rail grinding, and ballast screening blocks are requested by Sr.DEN/Civil for urgent track stabilization and speed restriction removal on high-density corridors:

| Job ID | Dept | Corridor | KM Span | Nature of Work | Duration | Permitted Window (IST) | Machinery Req | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| REQ-NR-001 | Engineering | NDLS-GZB | KM 12.5 to 20.0 | Continuous Track Tamping (CSM) | 180 min | 01:00 to 04:30 | Track Tamper TTM-401 | P1 |
| REQ-NR-002 | Electrical | NDLS-GZB | KM 14.0 to 22.0 | OHE 25kV Catenary Periodic Overhaul | 150 min | 01:30 to 04:30 | Tower Wagon TW-3 | P2 |
| REQ-NR-003 | S&T | NDLS-GZB | KM 16.0 to 18.5 | Point Machine Replacement & Testing | 90 min | 02:00 to 04:00 | S&T Testing Team | P3 |
| REQ-NR-004 | Engineering | NDLS-CNB | KM 45.0 to 58.0 | Rail Grinding (Speno Train) | 240 min | 00:30 to 05:00 | Speno Rail Grinder | P1 |
| REQ-NR-005 | Electrical | NDLS-CNB | KM 48.0 to 60.0 | Insulator Replacement & Power Isolation | 180 min | 01:00 to 04:30 | Tower Wagon TW-1 | P2 |
| REQ-NR-006 | Engineering | AGC-JHS | KM 110.0 to 125.0 | Deep Screening & Ballast Cleaning | 210 min | 01:00 to 05:00 | Ballast Cleaner BCM | P2 |
| REQ-NR-007 | S&T | AGC-JHS | KM 112.0 to 120.0 | Axle Counter Dual-Sensors Tuning | 120 min | 01:30 to 04:00 | S&T Testing Team | P3 |

# 2. Special Traffic & Train Precedence Guidelines

Train 12004 Vande Bharat Express on NDLS-CNB departing 06:00 arriving 11:30 (KM 0.0 to 440.0) has highest precedence. No maintenance block shall encroach beyond 05:00 IST on the NDLS-CNB mainline.

# 3. Unscheduled Emergency Works (Semi-Structured Memo)

Item E-91: Electrical traction department SSE/TRD requests emergency power block for broken dropper replacement on corridor HWH-KGP between KM 78.0 and 85.5 from 02:00 to 04:30 IST. Power block required. Priority 1.

Item E-92: P-Way gang requests 2.5 hour fishplate tightening on corridor HWH-KGP between KM 80.0 and 88.0 from 02:15 to 04:45 IST. Priority 2.